## Sheet1
| Date |  | Status
Task Name |  | Module
1. Balance confirmation new 5 task completed | 2024-06-10
1.all done task tested by me 2.Uplaod all code on server to balance confirmation | 2024-04-11
1. vsademo error fixed by me becouse old vsademo create enough error 1. Latest vsademo code created by me and upload on server | 2024-04-12
1. While reverting to a leave request option to Approve or Reject should be there in the List only. 2. after vsademo upload on server then all new task tested again like balance conf and vsa 4 new point that is done | 2024-04-13
1. While reverting to a leave request option to Approve or Reject should be there in the List only. 3. While reverting to a leave request option to Approve or Reject upload on server and tested by me | 2024-06-14
1.Balance confirmation bugs fixed total bugs was 6 2.employee code,client code and assignment code show on applyleave page | 2024-06-15
1.Balance conformation all code updated on live server by me and testing done 2.Under the Knowledge Base, you can access the files by clicking the "Subject" not by "File" column. | 2024-06-18
1.Assignment folder download problem 2.employee code display 3.knwoledge base modificaton created documntation and uplaod on vsademo 4.vsademo bugs fixed 4.1 Getting 'OOPs' error when clicking on 'My Timesheet' button. 4.2 Not able to fill the timesheet as Partner drop-down is showing blank. | 2024-06-19
1.assignment id 526 all totalhour fixed 2.oops error on assignment folder download 3.employee code after team login tab | 2024-06-20
1.employee code completed and starting partner ciode on portel | 2024-06-21
1.partner ciode on portel completed | 2024-06-24
1.employee code completed everywhre like admin ,partner,manager and staff and tested on all role id 2.completed document | 2024-06-25
1.employee code everywhre like admin ,partner,manager and staff (all code updated on vsademo ) 2.client want to hide offholidays client name from dropdown box it will be only show on sturday and holidays | 2024-06-26
1.client want to hide offholidays ( client name )from dropdown box it will be only show on sturday and holidays completed 2.Documentation | 2024-06-27
1.client want to display warning message on timesheet create page when user timesheet rejected 2.task no 27.1 , task no 18.2, approved count display on portal all this task upload on vsa live | 2024-06-28
1.vsademo database problem solved 2.client want to implement assignment view for user who is not work on that assignmnet 3.Employee code ,staff code and assignment code display on portal ready to uplaod on vsa live | 2024-06-29